## Sheet1
Risk | Response Strategy | Objectives | Baseline
|  |  | Likelihood | Impact | Risk Level
Lack of knowledge | Use UiPath forums to navigate around any issues, also can use the trainer if unable to find suitable solution using resources online. | Ensure timeline is met, able to finish project on time | Likely | Medium | 60%
Internet connection issues | Can use mobile as hotspot if available, also alert trainer as soon as possible. | Meet project schedules. | Unlikely | High | 70%
File errors, Application errors | Ensure files are pushed to github, so no files are lost and updates are not lost. | Prevent any losses. | Unlikely | High | 75%
Data stored compromised | Files should be password protected, sensitive information used through orchestrator. | Safety of user data | Unlikely | Medium | 80%
Inappropriate data gathered | Ensure that processes are robust with functions that check the validy of data gathered. | Information gathered is appropriate | Likely | Medium | 50%