## Sheet1
Risk | Risk Statement | Response Strategy | Objectives | Baseline
|  |  |  | Likelihood | Impact | Risk Level
Lack of knowledge, unable to complete tasks effectively. |  | Utilise the resources available such as online material, collegeus, trainer. | Spend extra time on areas I'm not comfortable with | Likely | Medium | 33%
Lack of time, unable to complete project. |  | Ensure project plans and deadlines are followed. | Deliverables are met | Unlikely | Low | 20%
Network Issues, preventing me from progression. |  | Inform technicians at earliest response, use mobile teathering in the meantime. |  | Unlikely | High | 80%
Laptop issues |  | Inform trainer ASAP, ensure all work is saved onto cloud and regularly updated so can be accessed from another device. | Have files ready to go to ensure I can progress. | Unlikely | Medium | 50%
File corruption |  | Ensure that I have 2 copies of files, one in git hub and one hard copy. |  | Unlikely | Medium | 50%

## Sheet2
| Due By | Complete By
Tasks
BOSCARD | 2020-06-16 | 2020-06-16
Overview of Project | 2020-06-16 | 2020-06-16
Risk Assessment | 2020-06-16 | 2020-06-17
Set up Github | 2020-06-16 | 2020-06-16
Requirements Gathering | 2020-06-16 | 2020-06-18
Split Proccesses into parts | 2020-06-18 | 2020-06-19
Review processes - current/desired state | 2020-06-18 | 2020-06-19
DPD | 2020-06-20
Definition of complete | 2020-06-20 | 2020-06-20
State Business logic | 2020-06-21
Complete User Reg Process | 2020-06-22 | 2020-06-22
Complete User Update Process | 2020-06-22 | 2020-06-23
Complete User remove Process | 2020-06-22 | 2020-06-23
Complete Sports Content Aggregation Process | 2020-06-23 | 2020-06-25
Complete Tech Content Aggregation Process | 2020-06-23 | 2020-06-25
Complete Book Content Aggregation Process | 2020-06-23 | 2020-06-25
Complete Report Content Aggregation Process | 2020-06-24
Delivery of Content | 2020-06-24
Make the Processes Robust, try/catches | 2020-06-24
Add config files | 2020-06-25
Bring the workflows together | 2020-06-25
Pesentation Prep | 2020-06-25